## Portfolio_Summary
LEMU TAJIN LAUNCH — PORTFOLIO HEALTH SUMMARY
Report generated: Thursday, 02 April 2026
Project | Overall RAG | Total Tasks | % Complete | Overdue Tasks
Supply Chain Readiness | Red | 12 | 52.5% | 2
Marketing Campaign Preparation | Amber | 14 | 56.8% | 2
Distributor & Retail Onboarding | Amber | 14 | 38.9% | 3

## Supply_Chain_Readiness
PROJECT HEALTH DASHBOARD — SUPPLY CHAIN READINESS
Week of 02 April 2026 ¦ Overall Status: |  |  |  | Red
Total Tasks | Completed | Avg % Complete | Overdue | Blocked
12 | 3 | 52.5% | 2 | 1
Task ID | Task Name | Owner | Start | End Date | Status | % Done | RAG | Critical? | Comments
T001 | Finalize packaging design | Rahim | 02/02/26 | 06/02/26 | Completed | 100% | Green | ★ YES | Design approved by brand team.
T002 | Approve packaging with legal & compliance | Nadia | 07/02/26 | 11/02/26 | Completed | 100% | Green | ★ YES | Regulatory text and claims cleared.
T003 | Confirm raw material suppliers | Imran | 08/02/26 | 13/02/26 | Completed | 100% | Green |  | Primary ingredient and can suppliers confirmed.
T004 | Place production order with co-packer | Karim | 14/02/26 | 20/03/26 | In Progress | 80% | Red | ★ YES | Commercial terms agreed; PO awaiting final operations sign-off.
T005 | Quality assurance testing — batch 1 | Sadia | 28/03/26 | 02/04/26 | In Progress | 55% | Amber | ★ YES | Initial stability and taste tests are running.
T006 | QA sign-off and certification | Jamil | 31/03/26 | 07/04/26 | Blocked | 20% | Red | ★ YES | Blocked pending external lab certificate.
T007 | Arrange 3PL warehouse partner | Mitu | 24/03/26 | 08/04/26 | In Progress | 65% | Green |  | Final warehouse rate card under review.
T008 | First inventory dispatch to regional warehouse | Rahim | 08/04/26 | 12/04/26 | Not Started | 0% | Green | ★ YES | Will begin after QA release and warehouse confirmation.
T009 | Stock availability confirmation — North region | Karim | 13/04/26 | 15/04/26 | Not Started | 0% | Green | ★ YES | Awaiting dispatch completion.
T010 | Stock availability confirmation — South region | Nadia | 13/04/26 | 15/04/26 | Not Started | 0% | Green |  | Awaiting dispatch completion.
T011 | Cold chain logistics setup | Imran | 04/04/26 | 11/04/26 | In Progress | 60% | Green |  | Cold storage routing plan is being finalized.
T012 | Inventory management system update | Sadia | 05/04/26 | 14/04/26 | In Progress | 50% | Green |  | SKU master creation in progress.
⚠ ATTENTION REQUIRED — OVERDUE & BLOCKED TASKS
T004 | Place production order with co-packer | Karim | 13d late | Commercial terms agreed; PO awaiting final operations sign-off. |  |  | Red
T005 | Quality assurance testing — batch 1 | Sadia | In Progress | Initial stability and taste tests are running. |  |  | Amber
T006 | QA sign-off and certification | Jamil | Blocked | Blocked pending external lab certificate. |  |  | Red

## Marketing_Campaign_Preparation
PROJECT HEALTH DASHBOARD — MARKETING CAMPAIGN PREPARATION
Week of 02 April 2026 ¦ Overall Status: |  |  |  | Amber
Total Tasks | Completed | Avg % Complete | Overdue | Blocked
14 | 2 | 56.8% | 2 | 1
Task ID | Task Name | Owner | Start | End Date | Status | % Done | RAG | Critical? | Comments
T013 | Finalize brand identity and style guide | Farah | 03/02/26 | 09/02/26 | Completed | 100% | Green |  | Brand assets and tone of voice approved.
T014 | Shoot product photography | Tariq | 10/02/26 | 14/02/26 | Completed | 100% | Green |  | Hero shots and pack shots delivered.
T015 | Develop TV/digital ad creative | Lamia | 15/02/26 | 05/04/26 | In Progress | 85% | Green |  | Creative is in final edit for multiple formats.
T016 | Get ad creative approved by legal | Noman | 10/03/26 | 26/03/26 | In Progress | 70% | Red |  | Awaiting final legal sign-off, one round of revisions remaining
T017 | Book media placements (TV, digital, OOH) | Farah | 31/03/26 | 03/04/26 | In Progress | 45% | Amber |  | Media partners shortlisted; bookings not yet locked.
T018 | Influencer outreach and contracting | Tariq | 20/03/26 | 09/04/26 | Blocked | 25% | Amber |  | Blocked while waiting for approved talent contracts.
T019 | Launch social media accounts | Lamia | 16/03/26 | 10/04/26 | In Progress | 65% | Green |  | Handles reserved; content calendar under upload.
T020 | Build campaign landing page | Noman | 18/03/26 | 12/04/26 | In Progress | 60% | Green |  | Page build is underway with analytics tags pending.
T021 | Email campaign to existing customer base | Farah | 29/03/26 | 01/04/26 | In Progress | 60% | Red |  | Audience list prepared; final creative still being inserted.
T022 | In-store display materials design | Tariq | 12/03/26 | 08/04/26 | In Progress | 75% | Green |  | Designs are in final artwork adjustments.
T023 | In-store display materials printing and delivery | Lamia | 09/04/26 | 13/04/26 | Not Started | 0% | Green |  | Printing to start after artwork release.
T024 | Press release drafting | Noman | 22/03/26 | 09/04/26 | In Progress | 70% | Green |  | Draft approved internally; polishing key quotes.
T025 | Press release distribution | Farah | 10/04/26 | 14/04/26 | Not Started | 0% | Green |  | Newswire distribution scheduled after final PR sign-off.
T026 | Launch event planning and execution | Tariq | 01/04/26 | 20/04/26 | In Progress | 40% | Green |  | Venue hold confirmed; production plan in development.
⚠ ATTENTION REQUIRED — OVERDUE & BLOCKED TASKS
T016 | Get ad creative approved by legal | Noman | 7d late | Awaiting final legal sign-off, one round of revisions remaining |  |  | Red
T017 | Book media placements (TV, digital, OOH) | Farah | In Progress | Media partners shortlisted; bookings not yet locked. |  |  | Amber
T018 | Influencer outreach and contracting | Tariq | Blocked | Blocked while waiting for approved talent contracts. |  |  | Amber
T021 | Email campaign to existing customer base | Farah | 1d late | Audience list prepared; final creative still being inserted. |  |  | Red

## Distributor_&_Retail_Onboardin
PROJECT HEALTH DASHBOARD — DISTRIBUTOR & RETAIL ONBOARDING
Week of 02 April 2026 ¦ Overall Status: |  |  |  | Amber
Total Tasks | Completed | Avg % Complete | Overdue | Blocked
14 | 1 | 38.9% | 3 | 1
Task ID | Task Name | Owner | Start | End Date | Status | % Done | RAG | Critical? | Comments
T027 | Identify and shortlist distributors | Arif | 04/02/26 | 12/02/26 | Completed | 100% | Green |  | Priority distributors shortlisted by territory.
T028 | Distributor pitch presentations | Maya | 13/02/26 | 31/03/26 | In Progress | 90% | Red |  | Final presentation round is scheduled for tomorrow.
T029 | Sign distributor agreements — Tier 1 | Rafi | 21/02/26 | 24/03/26 | In Progress | 75% | Red |  | Two contracts pending final commercial approval.
T030 | Sign distributor agreements — Tier 2 | Nila | 01/03/26 | 10/04/26 | In Progress | 55% | Green |  | Negotiations continue with secondary territories.
T031 | Train distributor sales teams | Arif | 06/04/26 | 15/04/26 | Not Started | 0% | Green |  | Training deck will be deployed once agreements are signed.
T032 | Negotiate shelf space with key retail chains | Maya | 05/03/26 | 27/03/26 | In Progress | 65% | Red |  | Retailers requested updated margin proposal; talks extended.
T033 | Confirm planogram placement | Rafi | 28/03/26 | 09/04/26 | In Progress | 50% | Green |  | Store-level placement options are being aligned.
T034 | Retail staff product training | Nila | 31/03/26 | 04/04/26 | In Progress | 50% | Amber |  | Training sessions drafted but attendance slots still open.
T035 | Set up trade promotion terms | Arif | 20/03/26 | 08/04/26 | Blocked | 20% | Amber |  | Blocked until Tier 1 commercial terms are finalized.
T036 | Point-of-sale material delivery to retailers | Maya | 07/04/26 | 13/04/26 | Not Started | 0% | Green |  | Delivery will start after print materials arrive.
T037 | First purchase orders from distributors | Rafi | 09/04/26 | 14/04/26 | Not Started | 0% | Green |  | Orders expected after contract closure.
T038 | Distributor portal access setup | Nila | 30/03/26 | 02/04/26 | In Progress | 40% | Amber |  | User accounts being prepared for onboarding.
T039 | Retail audit — pre-launch check | Arif | 13/04/26 | 17/04/26 | Not Started | 0% | Green |  | Audit checklist prepared for pre-launch visits.
T040 | Go-live confirmation from top 3 retailers | Maya | 18/04/26 | 20/04/26 | Not Started | 0% | Green |  | Final go-live confirmation planned on launch weekend.
⚠ ATTENTION REQUIRED — OVERDUE & BLOCKED TASKS
T028 | Distributor pitch presentations | Maya | 2d late | Final presentation round is scheduled for tomorrow. |  |  | Red
T029 | Sign distributor agreements — Tier 1 | Rafi | 9d late | Two contracts pending final commercial approval. |  |  | Red
T032 | Negotiate shelf space with key retail chains | Maya | 6d late | Retailers requested updated margin proposal; talks extended. |  |  | Red
T034 | Retail staff product training | Nila | In Progress | Training sessions drafted but attendance slots still open. |  |  | Amber
T035 | Set up trade promotion terms | Arif | Blocked | Blocked until Tier 1 commercial terms are finalized. |  |  | Amber
T038 | Distributor portal access setup | Nila | In Progress | User accounts being prepared for onboarding. |  |  | Amber