## Tasks
Task_ID | Task_Name | Project_Name | Owner | Start_Date | Planned_End_Date | Actual_Completion_Date | Status | Priority | Dependencies | Pct_Complete | Comments
T001 | Finalize packaging design | Supply Chain Readiness | Rahim | 2026-02-02 | 2026-02-06 | 2026-02-05 | Completed | High |  | 100 | Design approved by brand team.
T002 | Approve packaging with legal & compliance | Supply Chain Readiness | Nadia | 2026-02-07 | 2026-02-11 | 2026-02-11 | Completed | High | T001 | 100 | Regulatory text and claims cleared.
T003 | Confirm raw material suppliers | Supply Chain Readiness | Imran | 2026-02-08 | 2026-02-13 | 2026-02-12 | Completed | High |  | 100 | Primary ingredient and can suppliers confirmed.
T004 | Place production order with co-packer | Supply Chain Readiness | Karim | 2026-02-14 | 2026-03-20 |  | In Progress | High | T002,T003 | 80 | Commercial terms agreed; PO awaiting final operations sign-off.
T005 | Quality assurance testing — batch 1 | Supply Chain Readiness | Sadia | 2026-03-28 | 2026-04-02 |  | In Progress | High | T004 | 55 | Initial stability and taste tests are running.
T006 | QA sign-off and certification | Supply Chain Readiness | Jamil | 2026-03-31 | 2026-04-07 |  | Blocked | High | T005 | 20 | Blocked pending external lab certificate.
T007 | Arrange 3PL warehouse partner | Supply Chain Readiness | Mitu | 2026-03-24 | 2026-04-08 |  | In Progress | Medium |  | 65 | Final warehouse rate card under review.
T008 | First inventory dispatch to regional warehouse | Supply Chain Readiness | Rahim | 2026-04-08 | 2026-04-12 |  | Not Started | High | T006,T007 | 0 | Will begin after QA release and warehouse confirmation.
T009 | Stock availability confirmation — North region | Supply Chain Readiness | Karim | 2026-04-13 | 2026-04-15 |  | Not Started | Medium | T008 | 0 | Awaiting dispatch completion.
T010 | Stock availability confirmation — South region | Supply Chain Readiness | Nadia | 2026-04-13 | 2026-04-15 |  | Not Started | Medium | T008 | 0 | Awaiting dispatch completion.
T011 | Cold chain logistics setup | Supply Chain Readiness | Imran | 2026-04-04 | 2026-04-11 |  | In Progress | Medium | T007 | 60 | Cold storage routing plan is being finalized.
T012 | Inventory management system update | Supply Chain Readiness | Sadia | 2026-04-05 | 2026-04-14 |  | In Progress | Medium | T004 | 50 | SKU master creation in progress.
T013 | Finalize brand identity and style guide | Marketing Campaign Preparation | Farah | 2026-02-03 | 2026-02-09 | 2026-02-08 | Completed | High |  | 100 | Brand assets and tone of voice approved.
T014 | Shoot product photography | Marketing Campaign Preparation | Tariq | 2026-02-10 | 2026-02-14 | 2026-02-13 | Completed | Medium | T013 | 100 | Hero shots and pack shots delivered.
T015 | Develop TV/digital ad creative | Marketing Campaign Preparation | Lamia | 2026-02-15 | 2026-04-05 |  | In Progress | High | T013 | 85 | Creative is in final edit for multiple formats.
T016 | Get ad creative approved by legal | Marketing Campaign Preparation | Noman | 2026-03-10 | 2026-03-26 |  | In Progress | High | T015 | 70 | Awaiting final legal sign-off, one round of revisions remaining
T017 | Book media placements (TV, digital, OOH) | Marketing Campaign Preparation | Farah | 2026-03-31 | 2026-04-03 |  | In Progress | High | T016 | 45 | Media partners shortlisted; bookings not yet locked.
T018 | Influencer outreach and contracting | Marketing Campaign Preparation | Tariq | 2026-03-20 | 2026-04-09 |  | Blocked | Medium | T013 | 25 | Blocked while waiting for approved talent contracts.
T019 | Launch social media accounts | Marketing Campaign Preparation | Lamia | 2026-03-16 | 2026-04-10 |  | In Progress | Medium | T013 | 65 | Handles reserved; content calendar under upload.
T020 | Build campaign landing page | Marketing Campaign Preparation | Noman | 2026-03-18 | 2026-04-12 |  | In Progress | High | T013,T015 | 60 | Page build is underway with analytics tags pending.
T021 | Email campaign to existing customer base | Marketing Campaign Preparation | Farah | 2026-03-29 | 2026-04-01 |  | In Progress | Medium | T019,T020 | 60 | Audience list prepared; final creative still being inserted.
T022 | In-store display materials design | Marketing Campaign Preparation | Tariq | 2026-03-12 | 2026-04-08 |  | In Progress | Medium | T013 | 75 | Designs are in final artwork adjustments.
T023 | In-store display materials printing and delivery | Marketing Campaign Preparation | Lamia | 2026-04-09 | 2026-04-13 |  | Not Started | Medium | T022 | 0 | Printing to start after artwork release.
T024 | Press release drafting | Marketing Campaign Preparation | Noman | 2026-03-22 | 2026-04-09 |  | In Progress | Low | T013 | 70 | Draft approved internally; polishing key quotes.
T025 | Press release distribution | Marketing Campaign Preparation | Farah | 2026-04-10 | 2026-04-14 |  | Not Started | Low | T024 | 0 | Newswire distribution scheduled after final PR sign-off.
T026 | Launch event planning and execution | Marketing Campaign Preparation | Tariq | 2026-04-01 | 2026-04-20 |  | In Progress | Medium | T017,T025 | 40 | Venue hold confirmed; production plan in development.
T027 | Identify and shortlist distributors | Distributor & Retail Onboarding | Arif | 2026-02-04 | 2026-02-12 | 2026-02-11 | Completed | High |  | 100 | Priority distributors shortlisted by territory.
T028 | Distributor pitch presentations | Distributor & Retail Onboarding | Maya | 2026-02-13 | 2026-03-31 |  | In Progress | High | T027 | 90 | Final presentation round is scheduled for tomorrow.
T029 | Sign distributor agreements — Tier 1 | Distributor & Retail Onboarding | Rafi | 2026-02-21 | 2026-03-24 |  | In Progress | High | T028 | 75 | Two contracts pending final commercial approval.
T030 | Sign distributor agreements — Tier 2 | Distributor & Retail Onboarding | Nila | 2026-03-01 | 2026-04-10 |  | In Progress | Medium | T028 | 55 | Negotiations continue with secondary territories.
T031 | Train distributor sales teams | Distributor & Retail Onboarding | Arif | 2026-04-06 | 2026-04-15 |  | Not Started | Medium | T029,T030 | 0 | Training deck will be deployed once agreements are signed.
T032 | Negotiate shelf space with key retail chains | Distributor & Retail Onboarding | Maya | 2026-03-05 | 2026-03-27 |  | In Progress | High | T028 | 65 | Retailers requested updated margin proposal; talks extended.
T033 | Confirm planogram placement | Distributor & Retail Onboarding | Rafi | 2026-03-28 | 2026-04-09 |  | In Progress | Medium | T032 | 50 | Store-level placement options are being aligned.
T034 | Retail staff product training | Distributor & Retail Onboarding | Nila | 2026-03-31 | 2026-04-04 |  | In Progress | Medium | T030 | 50 | Training sessions drafted but attendance slots still open.
T035 | Set up trade promotion terms | Distributor & Retail Onboarding | Arif | 2026-03-20 | 2026-04-08 |  | Blocked | High | T029 | 20 | Blocked until Tier 1 commercial terms are finalized.
T036 | Point-of-sale material delivery to retailers | Distributor & Retail Onboarding | Maya | 2026-04-07 | 2026-04-13 |  | Not Started | Medium | T023,T029 | 0 | Delivery will start after print materials arrive.
T037 | First purchase orders from distributors | Distributor & Retail Onboarding | Rafi | 2026-04-09 | 2026-04-14 |  | Not Started | High | T029,T030 | 0 | Orders expected after contract closure.
T038 | Distributor portal access setup | Distributor & Retail Onboarding | Nila | 2026-03-30 | 2026-04-02 |  | In Progress | Low | T029 | 40 | User accounts being prepared for onboarding.
T039 | Retail audit — pre-launch check | Distributor & Retail Onboarding | Arif | 2026-04-13 | 2026-04-17 |  | Not Started | Medium | T034,T036,T038 | 0 | Audit checklist prepared for pre-launch visits.
T040 | Go-live confirmation from top 3 retailers | Distributor & Retail Onboarding | Maya | 2026-04-18 | 2026-04-20 |  | Not Started | High | T037,T039 | 0 | Final go-live confirmation planned on launch weekend.